## Product Backlog
US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
1 | As an administrator, I want to configure an online examination with questions and a time limit so that candidates can complete a controlled assessment. | Must | Examination/database models | Gunti Usha Sri | Completed
2 | As a candidate, I want to register and log in securely so that I can access my examination. | Must | User authentication/database | Gunti Usha Sri | Completed
3 | As a candidate, I want to complete pre-assessment camera and face validation so that the monitoring setup is verified before the examination. | Must | Camera service; OpenCV | Gunti Usha Sri | Completed
4 | As a candidate, I want examination questions and answer options displayed clearly so that I can complete the assessment properly. | Must | Question bank; examination session | Gunti Usha Sri | Completed
5 | As a candidate, I want my answers saved while navigating between questions so that my responses are not lost. | Must | Session management; database | Gunti Usha Sri | Completed
6 | As an invigilator, I want browser activity and focus events monitored so that suspicious examination behaviour can be detected. | Must | Browser monitoring; event logging | Gunti Usha Sri | Completed
7 | As an invigilator, I want no-face and multiple-face events detected so that possible integrity violations can be identified. | Must | Camera service; OpenCV | Gunti Usha Sri | Completed
8 | As an invigilator, I want tab switching, fullscreen exit and copy/paste activities monitored so that suspicious actions can be recorded. | Must | Browser event monitoring | Gunti Usha Sri | Completed
9 | As an invigilator, I want violation events recorded with timestamps so that examination behaviour can be reviewed later. | Must | Violation/event database | Gunti Usha Sri | Completed
10 | As an invigilator, I want an integrity score and risk level generated from detected violations so that examination sessions can be classified. | Must | Violation weights; session data | Gunti Usha Sri | Completed
11 | As an invigilator, I want monitoring evidence captured for relevant violations so that suspicious events can be reviewed. | Must | Camera service; evidence storage | Gunti Usha Sri | Completed
12 | As an analyst, I want examination session data summarized and visualized so that candidate performance and integrity behaviour can be analysed. | Should | Session/violation records; Pandas | Gunti Usha Sri | Completed
13 | As an analyst, I want K-Means clustering and risk analysis applied to examination sessions so that behavioural groups can be identified. | Should | Pandas/NumPy; scikit-learn | Gunti Usha Sri | Completed
14 | As an invigilator, I want an AI-assisted integrity report generated with a fallback option so that examination findings can be reported reliably. | Could | AI service; analytics | Gunti Usha Sri | Completed
15 | As an administrator, I want examination results and integrity reports exported in downloadable formats so that records can be shared and archived. | Should | Report generation; PDF/CSV | Gunti Usha Sri | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Original Estimate (Hours) | Effort (Hours) | Team Member | Activity | Status
1 | 1 | Design examination flow, session structure and database entities | 2026-08-17 | 6 | 6 | Gunti Usha Sri | Development | Completed
2 | 2 | Implement candidate registration, login and examination access | 2026-08-18 | 8 | 8 | Gunti Usha Sri | Development | Completed
3 | 3 | Implement examination questions, timer, navigation and answer handling | 2026-08-19 | 10 | 10 | Gunti Usha Sri | Development | Completed
6 | 4 | Implement tab switch, focus loss and browser activity monitoring | 2026-08-20 | 10 | 10 | Gunti Usha Sri | Development | Completed
3 | 5 | Implement camera validation and face monitoring using OpenCV | 2026-08-21 | 10 | 10 | Gunti Usha Sri | Development | Completed
7 | 6 | Implement no-face and multiple-face detection and violation logging | 2026-08-24 | 8 | 8 | Gunti Usha Sri | Development | Completed
10 | 7 | Implement integrity score calculation and risk classification | 2026-08-25 | 8 | 8 | Gunti Usha Sri | Development | Completed
12 | 8 | Implement Pandas analytics and examination data visualizations | 2026-08-26 | 8 | 8 | Gunti Usha Sri | Data Analysis | Completed
13 | 9 | Implement K-Means clustering and risk-based session analysis | 2026-08-27 | 8 | 8 | Gunti Usha Sri | Data Science | Completed
14 | 10 | Implement AI-assisted integrity report generation with fallback | 2026-08-28 | 6 | 6 | Gunti Usha Sri | AI Integration | Completed

## Stand up Meeting
Sprint Day | Date | Impediments | Action Taken
1 | 2026-08-17 | Initial integration of examination, monitoring and database components required coordination. | Set up the project structure, reviewed dependencies and defined the integration sequence.
2 | 2026-08-18 | Candidate authentication and examination access required proper session handling. | Implemented registration/login flow and verified authenticated examination access.
3 | 2026-08-19 | Examination navigation and answer handling needed reliable state synchronization. | Implemented question navigation, timer and answer handling and verified session state.
4 | 2026-08-20 | Browser tab switching and focus events needed to be recorded without duplicate violations. | Separated browser monitoring events and validated event logging behaviour.
5 | 2026-08-21 | Camera service compatibility and face validation required refinement. | Configured camera monitoring with OpenCV and validated face detection behaviour.
6 | 2026-08-24 | No-face and multiple-face events needed consistent violation recording. | Implemented face-event handling and verified violation records.
7 | 2026-08-25 | Integrity scoring required consistent violation weights and risk thresholds. | Implemented integrity score calculation and validated low, medium and high-risk cases.
8 | 2026-08-26 | Analytics required consistent session-level data for meaningful visualizations. | Prepared Pandas summaries and validated examination analytics and visualization inputs.
9 | 2026-08-27 | Clustering required normalized behavioural features for meaningful grouping. | Applied K-Means to session features and validated risk/cohort analysis.
10 | 2026-08-28 | AI report generation required reliable output when the external AI service was unavailable. | Implemented fallback report generation and validated representative integrity reports.

## Retrospection
Sprint | Start Date | End Date | What Went Well | What Could Be Improved | Continue Doing | Action Taken
1 | 2026-08-17 | 2026-08-21 | Core examination flow, candidate access, question handling and initial monitoring components were integrated successfully. | Camera and browser-monitoring dependencies required additional validation during integration. | Continue validating each monitoring component immediately after integration. | Validate camera, browser and examination flows using representative test sessions.
2 | 2026-08-24 | 2026-08-28 | Integrity scoring, violation detection, analytics, clustering and AI-assisted reporting were integrated successfully. | Analytics and AI reporting required fallback handling and consistent session-level data. | Continue using incremental testing with representative examination sessions. | Validate low/medium/high-risk sessions, analytics outputs and AI fallback reporting.