## Defect Tracker
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 | Gunti Usha Sri | 2026-09-08 | Webcam initialization could fail when camera permission was unavailable, leaving the examination monitoring state inconsistent. | Sprint 1 | Gunti Usha Sri | Functional | Added camera availability handling and a clear permission/error state before starting the monitoring session. | 2026-09-08 | Closed | Camera access is now validated before monitoring begins.
2 | Gunti Usha Sri | 2026-09-09 | Face-missing events could be triggered repeatedly while the candidate was briefly outside the camera frame. | Sprint 2 | Gunti Usha Sri | Logical | Introduced a continuous absence interval check so an event is recorded only after the configured threshold is exceeded. | 2026-09-09 | Closed | Face-absence monitoring now uses a threshold-based interval.
3 | Gunti Usha Sri | 2026-09-10 | Integrity score values were not consistently recalculated after monitoring events changed during an active session. | Sprint 2 | Gunti Usha Sri | Logical | Centralized score recalculation using the scoring module and updated the monitor state after event changes. | 2026-09-10 | Closed | Score, risk level, and event penalties are now calculated from the same metrics.
4 | Gunti Usha Sri | 2026-09-11 | Browser activity events such as tab switching and focus loss were not reliably reflected when the event request failed. | Sprint 2 | Gunti Usha Sri | Maintainability | Added client-side error handling and verified the browser-event logging route and database persistence. | 2026-09-11 | Closed | Browser monitoring failures no longer interrupt the examination flow.
5 | Gunti Usha Sri | 2026-09-12 | AI-generated integrity summaries could become unavailable when the external AI service or API key was not available. | Sprint 3 | Gunti Usha Sri | Compatibility | Implemented a deterministic fallback summary so reports can still be generated without an external AI response. | 2026-09-12 | Closed | Report generation remains available in offline/API-failure conditions.
6 | Gunti Usha Sri | 2026-09-13 | Evidence snapshot storage required stronger session isolation to prevent incorrect file references during candidate review. | Sprint 3 | Gunti Usha Sri | Security | Added session-based evidence naming and path validation before storing and retrieving incident snapshots. | 2026-09-13 | Closed | Evidence files are associated with the corresponding examination session.
7 | Gunti Usha Sri | 2026-09-14 | Analytics processing could produce incomplete visualizations when session data contained missing or inconsistent values. | Sprint 3 | Gunti Usha Sri | Data Validation | Added dataset preparation and normalization before generating score distributions, heatmaps, and clustering outputs. | 2026-09-14 | Closed | Analytics charts are generated from cleaned and normalized session data.
8 | Gunti Usha Sri | 2026-09-15 | The final examination report needed consistent inclusion of academic results together with monitoring metrics and evidence. | Sprint 3 | Gunti Usha Sri | Standards | Updated the report generation flow to combine examination results, integrity metrics, risk level, and monitoring evidence in a single report. | 2026-09-15 | Closed | Final reports now provide a consolidated examination and integrity summary.

## Project Info
Project | ExamTrace
Project Title | Evidence-Based Examination Monitoring & Integrity Analysis System
Document | Defect Tracker
Prepared For | Project Documentation / Agile Submission